## Project Schedule
Project Schedule |  | September |  |  |  | October |  |  |  | November |  |  |  | Completed
| Week (#) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | In Progress
| Start date | 31/8 | 2016-06-09 | 13/9 | 21/9 | 28/10 | 2016-05-10 | 2016-12-10 | 19/10 | 26/11 | 2016-02-11 | 2016-07-11 | 16/11 | Planned
| End date | 2016-06-09 | 13/9 | 20/9 | 27/9 | 2016-04-10 | 2016-11-10 | 18/10 | 25/10 | 2016-01-11 | 2016-08-11 | 15/11 | 22/11 | Overdue
Activity | Progress | [12 empty] | Description
Development
Setup Laravel | 100% | [12 empty] | Download, install, configure and integrate with other platforms
Login functionality | 95% | [12 empty] | Register an account, login, logout functions
Database configuration | 100% | [12 empty] | Database created and working. Tables to be added as required
Set up API | 75% | [12 empty] | Working functions for API backend
Access share information | 75% | [12 empty] | Retrieve company list and share prices
Dashboard config | 75% | [12 empty] | Connect login to dashboard
View share information | 75% | [12 empty] | UI to browse and search companies, shares
Make transaction | 0% | [12 empty] | Buy and sell shares functions
Transaction UI | 0% | [12 empty] | UI for transactions
Account balance | 0% | [12 empty] | View current balance in dollars and current stock value
Account summary | 0% | [12 empty] | View shares in possession and average prices
Account info UI | 0%
View transaction history | 0% | [12 empty] | View list of transactions
View share graphs | 0%
Leaderboard | 0% | [12 empty] | Functions, data storage
Leaderboard UI | 0% | [12 empty] | UI, dashboard table
Documentation
Draft Project Charter | 100% | [12 empty] | Create and submit a draft project charter
Risk Register | 100% | [12 empty] | Record 10 risks in the Risk Register
Project Schedule | 100%
User Guide | 0%
Class diagram | 80%
Usage Scenario | 80%
Setup Guide | 100%
Technical Design Solution | 5%
Testing
Login Tests | 75% | [12 empty] | Test units, LeanTest
API Tests
Database Tests